## INC Schedule FEATURE
FRANK BOND DAY, WASH. DC
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 7pm |  | Freedom Forum
NEWS | ? | ext | Capitol? | 8pm | night | Reporter stands outside Capitol? reporting | 14
NEWS | ? | ext | Capitol? |  | night | Reporter stands outside Capitol? reporting | 14
End Day FB
Total Scenes |  | 2 | Total Pages |  | TOT HRS | 4
SATURDAY, SEPT. 13TH (NO FRANK V. / ZANUCK) |  |  |  | Sunrise: 6:45am | Sunset: 7:10pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 11AM
105 | 1.875 | int | RV Super | 12PM | day | J.reveals conspiracy to M.&K.,start self-destruct & time jump sequence | 1,2,3
107 | 0.375 | int | RV Super |  | day | Alarms go off,M.yells for J.,M.explains to K.,M.yells for J. again | 1,2,3?
114 | 0.75 | int | RV Super | 2PM | day | M.&K.&J. in RV flying thru time&space,waves & clouds,scan monitors | 1,2,3
116 | 0.125 | int | RV Super |  | day | M. hits gas, swerves by cars | 1,2,3
118 | 1.75 | int | RV Super | 3PM | day | J. explains conspiracy to M.&K., J. jumps back, M.&K. continue on w/ plan | 1,2,3
6A | 1 | int | RV Super | 5PM | day | M. & J. drive to K.'s work, trouble w/ fellow drivers | 1,3
|  |  | Lunch | 6PM
33 | 0.125 | ext | RV Super | 7PM | D/N | M.&J. finish up batt.,suddenly becomes night, C.U. computer & work on equip.,K. watches | 1,2,3
29*** | 1.25 | int | RV Super | 8PM | night | Supllies,J. fiddles w/ batt.,Red Bulls,K. waters garden,M. watches until Z. pulls up | 1,2,3,4***
31 | 0.125 | int | RV Super |  | night | M. sees Z.'s pic on monitor, M. goes to house | 1,2?,3
46A*** | 0.125 | int | RV Super |  | night | K.'s phone vibrates in RV Super | -
End Day 1 |  |  |  | 10PM
Total Scenes |  | 10 | Total Pages | 7.5 | TOT HRS | 11
SUNDAY, SEPT. 14TH |  |  |  | Sunrise: 6:45am | Sunset: 7:10pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 5AM
48D | 3.375 | ext | Prison | 6AM | day | REMAR explains his plot/conspiracy to J.,forces J. to help | 3,5
92 | 0.75 | ext | Parking Lot | 8AM | day | J.& Remar zap to parking lot,J.attacks Remar,Remar fights off,they get in Buick | 3,5
|  |  | Company Move | 9AM
|  |  | Set-Up | 10AM
|  |  | Lunch | 11AM
102 | 0.125 | ext | Near Field/Parking Lot | 12PM | day | Buick pulls near to parked RV Super in field | 3,5
93 | 0.25 | int | Buick | 1PM | day | Remar checks glove-box-device,100 miles from RV Super,J.starts car | 3,5
103 | 0.625 | int | Buick |  | day | Remar & J. find RV Super,plan meet M.,Remar threatens J.,J. gets out heads to RV | 3,5
106 | 0.125 | int | Buick |  | day | Remar watches J.,reads self-destruct sequence & happy,watches Jatt | 3,5
109 | 0.125 | int | Buick | 2PM | day | Remar's devices beep,he watches J.,J.gives thumbs up & climbs back in | 3,5
111 | 0.125 | int | Buick |  | day | Remar realizes J.'s plan,gets out Buick firing Ray-Gun | 5
121 | 0.25 | int | Buick |  | day | Remar reads device,starts engine,heads for Matap | 5
113 | 0.125 | ext | RV Super | 3PM | day | RV vanishes in front of Remar | 5
104 | 0.5 | I/E | RV Super | 4PM | day | J.approaches M.&K. in RV,they greet,enter RV Super | 1,2,3
108 | 0.125 | ext | RV Super | 5PM | day | J.smiles as he connects a device | 3
110*** | 0.25 | int | RV Super | 6PM | day | J. jumps in,activates mini-time jump,big roar,(M.starts engine?) | 1,2,3
112*** | 0.125 | int | RV Super |  | day | J. hit by laser blast,falls to floor,M. calls out | 1,2,3
End Day 2 |  |  |  | 7PM
Total Scenes |  | 14 | Total Pages | 6.875 | TOT HRS | 14
SATURDAY, SEPT. 20TH (NO TOM T. / JATT) |  |  |  | Sunrise: 6:50am | Sunset: 7:00pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 7AM
84 | 0.125 | ext | Frederick's House | 8AM | day | RV Super pulls up to Frederick's house | 1,2
85 | 1.125 | int | RV Super | 9AM | day | M.&K. talk about Fred,getting help,going on TV, relationship | 1,2
86 | 0.375 | ext | Frederick's Front Door | 10AM | day | K. rings doorbell,no answer,M.&K. walk off frame | 1,2
|  |  | Lunch | 11AM
87 | 3 | ext | Back @ Fred's House | 12PM | day | M.&K. talk to Fred,show him alien tech to convince him,& he agree to help | 1,2,9
94 | 2.25 | I/E | Fred's House | 3PM | day | Fred intros Amy to M.&K.,discuss TV,proves truth to Amy,they all agree | 1,2,9,10
100 | 1.125 | I/E | Field/Parking Lot | 6PM | dusk | M.&K.had long day,discuss Amy,K.tired & annoyed gets out,M. follows | 1,2
101 | 1.125 | ext | RV Super | 7PM | dusk | M.&K. walk along path/field,discuss relationships,followed by montage | 1,2
End Day 3 |  |  |  | 8PM
Total Scenes |  | 7 | Total Pages | 9.125 | TOT HRS | 13
SUNDAY, SEPT. 21ST |  |  |  | Sunrise: 6:50am | Sunset: 7:00pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 6PM
22A | 0.125 | ext | Stevens Hall | 7PM | day | Establishing Shot | -
9A | 0.625 | I/E | Stevens Hall / RV Super | 8PM | night/dusk | M.&J. wait outside in RV Super, wait for K. to leave work | 1,2,3
|  |  | Company Move | 9PM
|  |  | Set-Up | 10PM
10 | 1 | ext | Bar Parking Lot | 11PM | night/dusk | M. follows K. into parking lot, K. parks, M. parks | 1,2,3
1A | 0.125 | ext | Restaurant |  | night | Matap walking out of restaurant | 1
|  |  | Lunch | 12AM MID
|  |  | Company Move | 1AM
|  |  | Set-Up | 2AM
12A | 0.125 | ext | Kate's House | 3AM | night/dusk | K. pulls to her house, gets out, RV Super pulls into frame | 2
12B | 0.125 | int | RV Super | 4AM | night/dusk | M. watches K.,looks to J.,J. styles himself | 1,2,3
13 | 0.25 | int | RV Super |  | night | Close on monitor,M. looks at thermoheat of K. in house | 1,3
110*** | 0.25 | int | RV Super | 5AM | N @ D | J. jumps in,activates mini-time jump,big roar,(M.starts engine?) | 1,2,3
112*** | 0.125 | int | RV Super |  | N @ D | J. hit by laser blast,falls to floor,M. calls out | 1,2,3
End Day 4 |  |  |  | 6AM
Total Scenes |  | 9 | Total Pages | 2.75 | TOT HRS | 12
SATURDAY, SEPT. 27TH (NO TOM T. / JATT) |  |  |  | Sunrise: 7:00am | Sunset: 6:50pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 11AM
26 | 1.125 | int | Kate's Car | 12PM | day | K.&M. drive to strip mall, M. talks shit about Earth | 1,2
27 | 1.125 | I/E | Strip Mall | 1PM | day | K. cut-off by DICK, M. dematerializes Dick's car, they park | 1,2,17
28 | 1.125 | ext | Strip Mall | 2PM | day | K.&M. talk about humans & Earth while walk,Dick can't find car | 1,2,17
|  |  | Company Move | 3PM
|  |  | Set-Up | 4PM
|  |  | Lunch | 5PM
52A | 1 | int | RV Super | 6PM | D/N? | M.drives K.in passenger seat,her phone rings,she talks to Z. | 1,2
47 | 0.5 | int | RV Super | 7PM | night | M. carries battery in RV Super,K. follows,they see News Report | 1,2
47A | 0.5 | int | RV Super |  | night | M. looks over batt.,K.'s phone keeps buzzing,M. fiddles w/ another device,exits RV,K. follows | 1,2
78B | 0.125 | int | RV Super | 8PM | night | M.&K.see Harrison infront,"Pull Over!",red plasma blob | 1,2
78D | 0.125 | int | RV Super |  | night | K.turns to M.,"Did you kill him?","No." | 1,2
78F | 0.125 | int | RV Super |  | night | M.explains what did to Harrison & laughs | 1,2
48A | 0.375 | ext | RV Super | 9PM | night | M. shows K. picture of famous celebrity / alien to help spread message | 1,2
End Day 5 |  |  |  | 10PM
Total Scenes |  | 10 | Total Pages | 6.125 | TOT HRS | 11
SUNDAY, SEPT. 28TH (NO TOM T. / JATT) |  |  |  | Sunrise: 7:00am | Sunset: 6:50pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 11AM
122 | 0.25 | ext | TV Station HQ | 12PM | day | M.&K., Fred,Amy walk from RV to station HQ,threaten News Dir.& G.M. | 1,2,9,10
|  |  | Set-Up | 1PM
124 | 0.25 | int | TV Station Hallway | 2PM | day | Fred&Amy walk around corner in hallway,talk about fame,Remar in hall w/ Ray-Gun kills them | 5,9,10
126 | 2.75 | int | TV Station Hallway |  | day | Remar reveals truth about M.,M.&Remar argue,M.shoots Remar,Remar shoots back,M.&K. bolt | 1,2,5
|  |  | Lunch | 4PM
123 | 0.125 | int | TV Station Waiting Room | 5PM | day | M.&K. walk into waiting room,Fred &Amy stand by door,offer drink | 1,2,9,10
125 | 0.125 | int | TV Station Waiting Room | 6PM | day | M.&K. hear Remar's gun,pulls disrupter,opens door,K. follows M. out | 1,2
127 | 0.625 | int | TV Station Waiting Room | 7PM | day | M.&K.bolt,Remar rises,fires door & explodes,M.&Remar fight,M.fiddles w/ watch,M.&K. time jump | 1,2,5
129 | 0.625 | int | TV Station Waiting Room | 9PM | day | Remar stands waiting,M.&K. appear behind him,M.blasts Remar dead,K.dizzy,they leave | 1,2,5
20 | 0.125 | int | Building | 11PM | day | K. walks down corridor,scans badge,security camera shots | 2
21 | 0.125 | int | Lab |  | day | K. walks to circuit and turns it off | 2
End Day 6 |  |  |  | 12AM MID
Total Scenes |  | 9 | Total Pages | 5 | TOT HRS | 13
SATURDAY, OCT. 4TH (NO TOM T. / JATT) |  |  |  | Sunrise: 7:00am | Sunset: 6:40pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 6AM
39A | 0.125 | int | Dennehy's Office | 7AM | night | Dennehy notices something odd | 11
89 | 2 | int | Dennehy's Office | 8AM | day | Harrison & Dennehy discuss K. & Belinda,both drink | 8,11
90 | 0.125 | int | Hall @ Dennehy's Office | 10AM | day | Z.watches Harrison leave Dennehy's office | 4,8
|  |  | Company Move | 11AM
|  |  | Lunch | 12PM
|  |  | Set-Up | 1PM
119 | 0.75 | int | Belinda's Apt. | 2PM | day | Belinda & Troy work on tracking device,False Eureka, Zanuck arrives | 4,6,7
130 | 0.375 | int | Belinda's Apt. |  | D/N? | Z.,Belinda,& Troy stand around tracking device, it works, "Eureka!" | 4,6,7
120 | 0.125 | ext | Belinda's Apt. | 3PM | day | Harrison sits in car watching everyone in Belinda's Apt. | 4?,6?,7?,8
131 | 0.125 | ext | Belinda's Apt. |  | D/N? | Z.,Belinda,& Troy leave apt., Harrison watches | 4,6,7,8
|  |  | Company Move | 4PM
|  |  | Set-Up | 5PM
52B | 1 | int | Zanuck's Car | 6PM | D/N? | Z.drives,Belinda & Troy track,Z.talks to K.on cell | 4,6,7
46 | 0.125 | ext | Zanuck's House | 7PM | night | Z. tries to call K.,no answer | 4
78A | 0.375 | I/E | Harrison's Car | 8PM | night | Harrison follows RV,calls back-up,swerves infront of RV,turns on cop lights | 8
End Day 7 |  |  |  | 9PM
Total Scenes |  | 10 | Total Pages | 5.125 | TOT HRS | 15
SUNDAY, OCT. 5TH (NO TOM T. / JATT, NO G. NELSON) |  |  |  | Sunrise: 7:00am | Sunset: 6:40pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
|  |  | Set-Up | 7AM
99 | 0.5 | ext | Lab Building | 8AM | day | Belinda & Troy sneek out w/ device,person walks by,Harrison watches,B&T get in car,T.sits funny | 6,7,8
23 | 0.375 | int | Lab | 9AM | day | Close on schematics, Z. grabs cane, goes to battery drawer, batt. Missing, Z. surprised | 4
24 | 0.125 | int | Lab |  | day | Z. watches security footage of K. | 4
9? | 0.5 | int | Basement Lab Office | 10AM | day | K. yelling at Z., joke, Belinda & Troy watch scared | 2?,4,6,7
88 | 1.25 | int | Lab | 11AM | day | Z.& Belinda worry about K.,Z.sees military,orders for plasma scan | 4,6,7?
|  |  | Lunch | 12PM
95 | 2 | int | Lab | 1PM | day | Harrison takes K.'s stuff from office,Z.& Belinda discuss K.& tracking device | 4,6,7?,8
97 | 0.125 | int | Lab | 3PM | day | Belinda & Troy look over components for tracking device | 6,7
98 | 0.125 | int | Lab |  | day | Belinda looks at device,then to Troy, "This could work." | 6,7
96 | 0.125 | int | Security Room | 4PM | day | Harrison watches monitor w. Z. & Belinda on it | 4,6,7?,8
|  |  | Company Move | 5PM
|  |  | Set-Up | 6PM
29*** | 1.25 | int | RV Super | 7PM | night | Supllies,J. fiddles w/ batt.,Red Bulls,K. waters garden,M. watches until Z. pulls up | 1*,2*,3*,4
83 | 0.125 | ext | Kate's House | 9PM | night | Z. pulls up to K. house, RV Super gone, Z. pissed | 4,6?,7?
End Day 8 |  |  |  | 10PM
Total Scenes |  | 11 | Total Pages | 6.5 | TOT HRS | 15
SATURDAY, OCT. 11TH - GREEN SCREEN DAY |  |  |  | Sunrise: 7:10am | Sunset: 6:30pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
78E | 0.125 | I/E | Past-Time Field | 1 | D/N | Harrison sits in car in shock,in past,Pre-Historic / Period Time | 8
48B | 2.75 | int | Hospital Room | 3 | day | GRN SCRN - J. wakes in Hospital, DR. talks to him, shows Earth,discuss his daughter Geela | 3,25
48C | 3.25 | int | Prison | 3 | day | GRN SCRN - J. visits GEELA in prison,she explains conspiracy,they argue,J. leaves | 3,13?,18?19
91 | 2.25 | int | Time Jump Pad | 3 | day | GRN SCRN - J.& Remar step on Jump Pad,argue then jump back | 3,5
128 | 0.5 | int | Time Jump Pad | 1 | D/N | GRN SCRN - M.&K.appear on Jump Pad,TECH stunned,M.grabs huge new gun,M.&K. flash away again | 1,2,27
End Day 9
Total Scenes |  | 5 | Total Pages | 8.875 | TOT HRS | 11
SATURDAY, OCT. 18TH |  |  |  | Sunrise: 7:20am | Sunset: 6:20pm
Scene | Pages | INT/EXT | Location | Time | D/N | Description | Cast
MONT |  |  |  | 1 |  | SUPER RV driving around couple of hours to find Kate's Bldg. | -
|  |  | Company Move | 1
MONT | [5 empty] | SUPER RV follows Kate's RED ROVER to café | -
|  |  | Lunch | 1
65 | 0.125 | int | Office | 1 | night | Man in office watches Matt on computer | 26
69 | 0.125 | int | Office | 1 | night | Man in office continues to watch Matt on computer | 26
|  |  | Company Move | 1
60 | 0.125 | ext | Roof | 1 | night | Satellite dishes start to move slightly | -
115 | 0.125 | ext | RV Super | 1 | day | RV appears wrong way in oncoming traffic,tires screech,horns blare | -
117 | 0.125 | ext | RV Super | 1 | day | RV pulls to side of road | -
46A*** | 0.125 | int | RV Super | 1 | night | K.'s phone vibrates in RV Super | -
78C | 0.125 | ext | RV Super | 1 | night | Red plasma blob hits Harrison's car,it disappears,RV drives straight thru | -
78G | 0.125 | ext | RV Super | 1 | night | RV Super drives off | -
38 | 0.125 | ext | City Street | 1 | night | Various shots city lights going out, transformers exploding,cars going dead | -
39 | 0.125 | ext | Earth | 1 | D/N | Purple wave washes over Earth | -
1 | 0.125 | ext | Woods | 1 | day | Serene woods, then BOOM!, trees shake, leaves rattle | -
End Day PU 1
Total Scenes |  | 5 | Total Pages | 0.375 | TOT HRS | 9

## INC FEATURE Days OO Days
|  |  | Sat | Sun | Sat | Sun | Sat | Sun | Sat | Sun | Sat | Sat
Char. |  | DayFB | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | DayPU | TOTAL
Num. | Character | Aug | 2008-09-13 | 2008-09-14 | 2008-09-20 | 2008-09-21 | 2008-09-27 | 2008-09-28 | 2008-10-04 | 2008-10-05 | 2008-10-11 | 2008-10-18
1 | MATAP |  | SW | W | W | W | W | W |  |  | WF |  | 7
2 | KATE |  | SW | W | W | W | W | W |  |  | WF |  | 7
3 | JATT |  | 2008-09-13: SW; 2008-09-14: W; 2008-09-21: W; 2008-10-11: WF | 4
4 | ZANUCK | [11 empty] | 2 | bar: 2008-10-04 to 2008-10-05
5 | REMAR |  | 2008-09-14: SW; 2008-09-28: W; 2008-10-11: WF | 3
6 | BELINDA | [11 empty] | 2 | bar: 2008-10-04 to 2008-10-05
7 | TROY | [11 empty] | 2 | bar: 2008-10-04 to 2008-10-05
8 | HARRISON |  | 2008-10-04: SW; 2008-10-05: W; 2008-10-11: WF | 3
9 | FREDERICK | [11 empty] | 2 | bar: 2008-09-20; 2008-09-28
10 | AMY | [11 empty] | 2 | bar: 2008-09-20; 2008-09-28
11 | DENNEHY |  | 2008-10-04: SWF | 1
12 | REPORTER | [11 empty] | 0
13 | GUARD |  | 2008-10-11: SWF | 1
14 | FRANK BOND | SWF | [10 empty] | 1
15 | SECURITY GUARD | [11 empty] | 0
16 | OLDER KATE | [11 empty] | 0
17 | DICK ON THE CELL |  | 2008-09-27: SWF | 1
18 | GUARD TECH |  | 2008-10-11: SWF | 1
19 | GELLA |  | 2008-10-11: SWF | 1
20 | REPORTER #2 | [11 empty] | 0
21 | SON | [11 empty] | 0
22 | POLICE OFFICER | [11 empty] | 0
23 | BARTENDER | [11 empty] | 0
24 | [12 empty] | 0
25 | DOCTOR |  | 2008-10-11: SWF | 1
26 | MAN IN OFFICE |  | 2008-10-18: SWF | 1
27 | TECH |  | 2008-10-11: SWF | 1
X1 | FAMILY | [11 empty] | 0
0